Lucid Development Cadence
Scopes and Commitments

---
Nagging Questions
- Are we on track to deliver on our commitments?
- Are we building the right thing?

---
Preferred Mental States
Schedule
Applicability
- Known on track
- Known behind
- Suspect on track
- Suspected behind
- Know high
- Known low
- Suspected high
- Suspected low

---
Tracking of
Production
Computer
Programming
Writing
Math

---
Burn Down Charts
- Provide insight into work accomplished and remaining compared against time
- Require tracking state of work items
- Provide aggregated status, rather than status on individual items
- Light weight tool via Agile Programming

---
“Ideal” Burn Down Chart

---
Burn Down with “Steering”

---
Burn Down with Scope “Creep”

---
Automated Burn Down Charts in Lucid
https://code.edge.launchpad.net/~rick-rickspencer3/+junk/py-burndown-chart
Work Item
Blueprint
Work Item
Work Item
Work Item
Blueprint
Work Item
Work Item
Work Item
Blueprint
Work Item
Work Item

---
Some problems with 6 month commitments
- Things are harder or easier than expected
- Upstreams change schedules or focus
- Opportunity changes

---
What was the key theme of Karmic's Alpha 2?

---
Platform Team Commitment Setting in Lucid
- Commit to work for only one milestone at a time
- Re-plan commitments for the next milestone
- Map onto Lucid schedule
- Document work items and burn 'em down

---
Lucid Milestones
Initial Integration and Riskiest Work	Alpha 2	2010-01-14
Essential Development	Alpha 3	2010-02-25
Clean Up and Completion	Beta 2	2010-04-08